## By Project
Project | Item | Start Date | Start Week | Time | End Date | End Week | Days Left/Past | Complete: 1/7 | Completed On: | VizLink | Overdue: 0 | Item for Schedule | N-W Days Added
DO NOT CHANGE THIS ROW | [11 empty] | DO NOT CHANGE THIS ROW: | 0
Example 1 | Find Sources | 2024-01-01 | Week -2 | 28 | 2024-01-30 | Week 3 |  | 1 | 2024-01-06 | 🟦 |  | Example 1: Find Sources | 1
Example 1 | Write Lit Review | 2024-01-08 | Week -1 | 28 | 2024-02-06 | Week 4 | 6wks, 6d | 0.5 |  | 🟦 |  | Example 1: Write Lit Review | 1
Example 1 | Write Method | 2024-01-15 | Week 1 | 14 | 2024-01-30 | Week 3 | 5wks, 6d | 0.25 |  | 🟦 |  | Example 1: Write Method | 1
Example 1 | Write Results | 2024-02-05 | Week 4 | 21 | 2024-02-26 | Week 7 |  | Hold |  | 🟦 |  | Example 1: Write Results | 0
0
Example 2 | Find Sources | 2024-02-26 | Week 7 | 28 | 2024-03-25 | Week 11 | 13wks, 5d |  |  | 🟦 |  | Example 2: Find Sources | 0
Example 2 | Write Lit Review | 2024-03-04 | Week 8 | 28 | 2024-04-01 | Week 12 | 14wks, 5d |  |  | 🟦 |  | Example 2: Write Lit Review | 0
Example 2 | Write Method | 2024-03-11 | Week 9 | 14 | 2024-03-25 | Week 11 | 13wks, 5d |  |  | 🟦 |  | Example 2: Write Method | 0
Example 2 | Write Results | 2024-03-25 | Week 11 | 21 | 2024-04-15 | Week 14 | 16wks, 5d |  |  | 🟦 |  | Example 2: Write Results | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on F1: Nick Henry: End Date is colored orange if it is extended because of Non-Working Days. Note: This only accounts for Non-Working Days that fall within the original timeline (Start Date + Time). It does not account for NWDs that fall within the new, extended timeline (i.e., it is not recursive).
Note on A3: Henry, Nick: Enter your project and the to-do item in columns A & B. Then add the Start date in Column C. As needed, add the time needed to complete the project (in days) in column E.
Note on I3: Henry, Nick: As you complete items, enter their percentage complete (as a decimal, 1 = complete). You can also enter "Hold" if you would like the item temporarily removed from your weekly schedule. (This does not remove it from the visualization).
Note on K3: Henry, Nick: Click the box to go to the item on the visualization page.

## Weekly Schedule
N/A | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-08-01 | 2025-01-01 | 2025-05-01 | 2025-05-02
| Week -2 | Week -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Week +1 | Week +2 | SUMMER | SUMMER | SUMMER | FALL | SPRING 25 | SUMMER 25
1 | Example 1: Find Sources | Example 1: Write Lit Review | Example 1: Write Method | Example 1: Write Method | Example 1: Write Method | Example 1: Write Lit Review | None | None | Example 2: Find Sources | Example 2: Find Sources | Example 2: Find Sources | Example 2: Find Sources | Example 2: Find Sources | Example 2: Write Lit Review | Example 2: Write Results | Example 2: Write Results | None | None | None | None | None | None | None | None | None | None
2 | 2024-01-08: Example 1: Find Sources; 2024-01-15: Example 1: Write Lit Review; 2024-01-22: Example 1: Write Lit Review; 2024-01-29: Example 1: Write Lit Review; 2024-03-04: Example 2: Write Lit Review; 2024-03-11: Example 2: Write Lit Review; 2024-03-18: Example 2: Write Lit Review; 2024-03-25: Example 2: Write Lit Review; 2024-04-01: Example 2: Write Results
3 | 2024-01-15: Example 1: Find Sources; 2024-01-22: Example 1: Find Sources; 2024-01-29: Example 1: Find Sources; 2024-03-11: Example 2: Write Method; 2024-03-18: Example 2: Write Method; 2024-03-25: Example 2: Write Method
4 | 2024-03-25: Example 2: Write Results
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
1 | Example 1: Find Sources (-4) | Example 1: Write Lit Review (-4) | Example 1: Write Method (-2) | Example 1: Write Method (-1) | Complete Example 1: Write Method | Complete Example 1: Write Lit Review | None | None | Example 2: Find Sources (-4) | Example 2: Find Sources (-3) | Example 2: Find Sources (-2) | Example 2: Find Sources (-1) | Complete Example 2: Find Sources | Complete Example 2: Write Lit Review | Example 2: Write Results (-1) | Complete Example 2: Write Results | None | None | None | None | None | None | None | None | None | None
2 | 2024-01-08: Example 1: Find Sources (-3); 2024-01-15: Example 1: Write Lit Review (-3); 2024-01-22: Example 1: Write Lit Review (-2); 2024-01-29: Example 1: Write Lit Review (-1); 2024-03-04: Example 2: Write Lit Review (-4); 2024-03-11: Example 2: Write Lit Review (-3); 2024-03-18: Example 2: Write Lit Review (-2); 2024-03-25: Example 2: Write Lit Review (-1); 2024-04-01: Example 2: Write Results (-2)
3 | 2024-01-15: Example 1: Find Sources (-2); 2024-01-22: Example 1: Find Sources (-1); 2024-01-29: Complete Example 1: Find Sources; 2024-03-11: Example 2: Write Method (-2); 2024-03-18: Example 2: Write Method (-1); 2024-03-25: Complete Example 2: Write Method
4 | 2024-03-25: Example 2: Write Results (-3)
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Visualization
Project | Item | Start Date | Start Week | Time | End Date | End Week | Days Left/Past | Complete: 1/7 | Completed On: | VizLink | Overdue: 0 | Item | Link | Week -2 | Week -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Week +1 | Week +2 | SUMMER | SUMMER | SUMMER | FALL | SPRING 25 | SUMMER 25
Sorted By | Date | [12 empty] | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-08-01 | 2025-01-01 | 2025-05-01
DO NOT CHANGE THIS ROW | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Example 1 | Find Sources | 2024-01-01 | Week -2 | 28 | 2024-01-30 | Week 3 |  | 1 | 2024-01-06 | 🟦 |  | Example 1: Find Sources | 🟦 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Example 1 | Write Lit Review | 2024-01-08 | Week -1 | 28 | 2024-02-06 | Week 4 | 6wks, 6d | 0.5 |  | 🟦 |  | Example 1: Write Lit Review | 🟦 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Example 1 | Write Method | 2024-01-15 | Week 1 | 14 | 2024-01-30 | Week 3 | 5wks, 6d | 0.25 |  | 🟦 |  | Example 1: Write Method | 🟦 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Example 2 | Find Sources | 2024-02-26 | Week 7 | 28 | 2024-03-25 | Week 11 | 13wks, 5d |  |  | 🟦 |  | Example 2: Find Sources | 🟦 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Example 2 | Write Lit Review | 2024-03-04 | Week 8 | 28 | 2024-04-01 | Week 12 | 14wks, 5d |  |  | 🟦 |  | Example 2: Write Lit Review | 🟦 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Example 2 | Write Method | 2024-03-11 | Week 9 | 14 | 2024-03-25 | Week 11 | 13wks, 5d |  |  | 🟦 |  | Example 2: Write Method | 🟦 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Example 2 | Write Results | 2024-03-25 | Week 11 | 21 | 2024-04-15 | Week 14 | 16wks, 5d |  |  | 🟦 |  | Example 2: Write Results | 🟦 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Non-Working Days
Start | End | Length | Description
DO NOT CHANGE THIS ROW
2024-01-15 | 2024-01-16 | 1 | MLK Day

## Other
Week | Dates | Text to Copy | List for Data Validation
Week -2 | 01/01 | Week -2 (01/01) | 0
Week -1 | 01/08 | Week -1 (01/08) | 0.01
1 | 01/15 | Week 1 (01/15) | 0.02
2 | 01/22 | Week 2 (01/22) | 0.03
3 | 01/29 | Week 3 (01/29) | 0.04
4 | 02/05 | Week 4 (02/05) | 0.05
5 | 02/12 | Week 5 (02/12) | 0.06
6 | 02/19 | Week 6 (02/19) | 0.07
7 | 02/26 | Week 7 (02/26) | 0.08
8 | 03/04 | Week 8 (03/04) | 0.09
9 | 03/11 | Week 9 (03/11) | 0.1
10 | 03/18 | Week 10 (03/18) | 0.11
11 | 03/25 | Week 11 (03/25) | 0.12
12 | 04/01 | Week 12 (04/01) | 0.13
13 | 04/08 | Week 13 (04/08) | 0.14
14 | 04/15 | Week 14 (04/15) | 0.15
15 | 04/22 | Week 15 (04/22) | 0.16
16 | 04/29 | Week 16 (04/29) | 0.17
Week +1 | 05/06 | Week +1 (05/06) | 0.18
Week +2 | 05/13 | Week +2 (05/13) | 0.19
SUMMER | 05/20 | SUMMER (05/20) | 0.2
SUMMER | 05/27 | SUMMER (05/27) | 0.21
SUMMER | 06/03 | SUMMER (06/03) | 0.22
FALL | 08/01 | FALL (08/01) | 0.23
SPRING 25 | 01/01 | SPRING 25 (01/01) | 0.24
SUMMER 25 | 05/01 | SUMMER 25 (05/01) | 0.25
0.26
0.27
0.28
0.29
0.3
0.31
0.32
0.33
0.34
0.35
0.36
0.37
0.38
0.39
0.4
0.41
0.42
0.43
0.44
0.45
0.46
0.47
0.48
0.49
0.5
0.51
0.52
0.53
0.54
0.55
0.56
0.57
0.58
0.59
0.6
0.61
0.62
0.63
0.64
0.65
0.66
0.67
0.68
0.69
0.7
0.71
0.72
0.73
0.74
0.75
0.76
0.77
0.78
0.79
0.8
0.81
0.82
0.83
0.84
0.85
0.86
0.87
0.88
0.89
0.9
0.91
0.92
0.93
0.94
0.95
0.96
0.97
0.98
0.99
1
Done
Hold